## Slide 1: SOP of Execution of FDR works
To be followed by:
Contractor
Project Implementation Unit
Project Management Unit

## Slide 2
Stages:
Deployment of Manpower
Deployment of Manpower for Lab
Deployment of Manpower of Execution

## Slide 3
4. Deployment of Machineries:
  Reclaimer
  Cement Spreader & Additive Spreader
  Pat Foot Roller
  Tandum Roller/Soil Compactor
  Pneumatic Tyre Roller
  Water Tanker
  Motor Grader

## Slide 4
5. Arrangement of Additive:
Details of Additives required to be submitted by the contractor
  Brand Name and Manufacturer Detail
  IRC Accreditation or Equivalent Accreditation Certificate
  Leaching Test Report
  Procurement Detail of the Material (submitted to the PIU time to time).

## Slide 5
6. Submission of JMF
Following information is to be submitted to the PIU:
  MDD and OMC
  7th day and 28th day UCS
  Flexural Strength
  Durability
  Residual Strength

## Slide 6
7. Stagewise Activities of Work Execution
  1. Collection of Material Sample for JMF
  Responsible Person -PIU+PMU+Contractor
  2. Procurement and Evaluation of JMF
  Responsible Person -PIU+PMU
  3. Establishment of Information Sign board & Citizen Information Board
  Responsible Person –Contractor
  4. Setting of works - Establishment of Bench Mark (RBM/TBM)/ Reference Pillers
  Responsible Person –Contractor

## Slide 7
  5. Establishment of Central Laboratry and Packagewise Laboratories
  Responsible Person-Contractor
  6. Joint Survey of the road and CD structure
  Responsible Person - PIU & Contractor
  7. Finalization of Road level
  Responsible Person –PIU & Contractor
  8. Clearing & Grubbing
  Responsible Person –Contractor

## Slide 8
  9. Execution of Embankment and Subgrade
  Responsible Person-Contractor
  10. Dismentaling of Existing Pavement & Spreading in required width
  Responsible Person - Contractor
  11. Construction of Trial Patch
  Responsible Person –PIU & Contractor
  12. Execution of Stabilization work of remaining length
  Responsible Person–PIU, PMU & Contractor

## Slide 9
  13. Prime coat over FDR base
  Responsible Person-PIU & Contractor
  14. Tack Coat
  Responsible Person - Contractor
  15. Laying of SAMI Layer
  Responsible Person –PIU, PMU & Contractor
  16. Laying of Tack coat over SAMI layer under with BC
  Responsible Person–PIU, PMU & Contractor

## Slide 10
  17. Laying of BC
  Responsible Person- PIU, PMU & Contractor
  18. Speed braker as required
  Responsible Person - PIU & Contractor
  19. Construction of Side drain and paneled concrete pavement in the built up area.
  Responsible Person –PIU & Contractor
  20. Fixing of Caution Board & Village Boards, Logo Board, Fixing of Cateyes,. Marking of Edge Lines.
  Responsible Person–PIU & Contractor